## Sheet1
Task_ID | Process_Name | Task_Name | Owner | Department | Start_Date | Due_Date | Completion_Date | Status | Gap_Days | Impact
T001 | IT | Data Backup | Priya | Finance | 2025-09-20 | 2025-09-27 | 2025-09-26 | On-Time | -1 | High
T002 | IT | Vendor Request | Nisha | Procurement | 2025-09-01 | 2025-09-06 | 2025-09-09 | Delayed | 3 | Low
T003 | Approvals | Policy Review | David | IT | 2025-09-07 | 2025-09-10 | 2025-09-13 | Delayed | 3 | Low
T004 | Reporting | Vendor Request | David | IT | 2025-09-10 | 2025-09-17 | 2025-09-16 | On-Time | -1 | Low
T005 | Inventory | Data Backup | Nisha | Procurement | 2025-09-14 | 2025-09-19 | 2025-09-18 | On-Time | -1 | Low
T006 | IT | Update Stock DB | Sarah | Ops | 2025-09-16 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T007 | Approvals | Monthly Report | Sarah | Ops | 2025-09-06 | 2025-09-13 | 2025-09-14 | Delayed | 1 | Low
T008 | Procurement | Budget Approval | Sarah | Ops | 2025-09-14 | 2025-09-21 | 2025-09-22 | Delayed | 1 | Medium
T009 | Reporting | Vendor Request | John | IT | 2025-09-15 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Low
T010 | Procurement | Policy Review | John | IT | 2025-09-01 | 2025-09-07 | 2025-09-08 | Delayed | 1 | High
T011 | Approvals | Sprint Update | John | IT | 2025-09-09 | 2025-09-14 | 2025-09-15 | Delayed | 1 | Low
T012 | IT | System Audit | Alex | Ops | 2025-09-17 | 2025-09-21 | 2025-09-20 | On-Time | -1 | High
T013 | Approvals | Budget Approval | Nisha | Procurement | 2025-09-08 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Medium
T014 | Inventory | Vendor Request | John | IT | 2025-09-08 | 2025-09-14 | 2025-09-14 | On-Time | 0 | Medium
T015 | Procurement | Data Backup | Sarah | Ops | 2025-09-18 | 2025-09-25 | 2025-09-26 | Delayed | 1 | Medium
T016 | Procurement | Data Backup | John | IT | 2025-09-15 | 2025-09-20 | 2025-09-21 | Delayed | 1 | Medium
T017 | Reporting | Vendor Request | David | IT | 2025-09-07 | 2025-09-12 | 2025-09-11 | On-Time | -1 | Low
T018 | Procurement | Monthly Report | Priya | Finance | 2025-09-07 | 2025-09-13 | 2025-09-14 | Delayed | 1 | Low
T019 | Procurement | System Audit | Nisha | Procurement | 2025-09-10 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Medium
T020 | Reporting | Data Backup | Priya | Finance | 2025-09-10 | 2025-09-13 | 2025-09-16 | Delayed | 3 | High
T021 | IT | Update Stock DB | Alex | Ops | 2025-09-18 | 2025-09-23 | 2025-09-23 | On-Time | 0 | Low
T022 | Approvals | Vendor Request | Alex | Ops | 2025-09-19 | 2025-09-24 | 2025-09-26 | Delayed | 2 | Medium
T023 | Approvals | Data Backup | Priya | Finance | 2025-09-02 | 2025-09-07 | 2025-09-09 | Delayed | 2 | High
T024 | Inventory | Policy Review | Sarah | Ops | 2025-09-03 | 2025-09-10 | 2025-09-09 | On-Time | -1 | High
T025 | Reporting | Order Processing | John | IT | 2025-09-03 | 2025-09-07 | 2025-09-06 | On-Time | -1 | Low
T026 | Approvals | Order Processing | Nisha | Procurement | 2025-09-20 | 2025-09-24 | 2025-09-27 | Delayed | 3 | Medium
T027 | Approvals | Budget Approval | John | IT | 2025-09-19 | 2025-09-25 | 2025-09-26 | Delayed | 1 | Low
T028 | Procurement | Update Stock DB | Nisha | Procurement | 2025-09-04 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Medium
T029 | Inventory | Monthly Report | Priya | Finance | 2025-09-06 | 2025-09-13 | 2025-09-12 | On-Time | -1 | High
T030 | Inventory | Policy Review | Sarah | Ops | 2025-09-20 | 2025-09-26 | 2025-09-27 | Delayed | 1 | High
T031 | Reporting | Server Patch | David | IT | 2025-09-10 | 2025-09-16 | 2025-09-15 | On-Time | -1 | Low
T032 | Reporting | Server Patch | David | IT | 2025-09-19 | 2025-09-23 | 2025-09-25 | Delayed | 2 | High
T033 | Procurement | Sprint Update | David | IT | 2025-09-05 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T034 | Inventory | Monthly Report | John | IT | 2025-09-20 | 2025-09-27 | 2025-09-28 | Delayed | 1 | Medium
T035 | Inventory | Budget Approval | David | IT | 2025-09-10 | 2025-09-16 | 2025-09-17 | Delayed | 1 | Low
T036 | Procurement | Budget Approval | Sarah | Ops | 2025-09-03 | 2025-09-10 | 2025-09-09 | On-Time | -1 | Medium
T037 | IT | Order Processing | John | IT | 2025-09-01 | 2025-09-04 | 2025-09-04 | On-Time | 0 | Low
T038 | Procurement | Order Processing | Alex | Ops | 2025-09-09 | 2025-09-16 | 2025-09-15 | On-Time | -1 | High
T039 | Approvals | System Audit | David | IT | 2025-09-15 | 2025-09-20 | 2025-09-20 | On-Time | 0 | Low
T040 | Approvals | Budget Approval | Alex | Ops | 2025-09-16 | 2025-09-21 | 2025-09-23 | Delayed | 2 | Medium
T041 | IT | Vendor Request | Priya | Finance | 2025-09-11 | 2025-09-17 | 2025-09-19 | Delayed | 2 | Medium
T042 | Approvals | System Audit | Alex | Ops | 2025-09-15 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Medium
T043 | IT | Vendor Request | Sarah | Ops | 2025-09-17 | 2025-09-20 | 2025-09-23 | Delayed | 3 | Medium
T044 | Approvals | Update Stock DB | Priya | Finance | 2025-09-17 | 2025-09-22 | 2025-09-25 | Delayed | 3 | Medium
T045 | Approvals | Update Stock DB | Priya | Finance | 2025-09-09 | 2025-09-16 | 2025-09-16 | On-Time | 0 | Medium
T046 | Approvals | Budget Approval | Alex | Ops | 2025-09-01 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Low
T047 | Reporting | Server Patch | Nisha | Procurement | 2025-09-01 | 2025-09-08 | 2025-09-10 | Delayed | 2 | High
T048 | Reporting | Vendor Request | Sarah | Ops | 2025-09-04 | 2025-09-08 | 2025-09-10 | Delayed | 2 | Low
T049 | IT | System Audit | David | IT | 2025-09-09 | 2025-09-15 | 2025-09-17 | Delayed | 2 | Medium
T050 | Reporting | Budget Approval | Nisha | Procurement | 2025-09-05 | 2025-09-11 | 2025-09-11 | On-Time | 0 | Low
T051 | Procurement | Monthly Report | Alex | Ops | 2025-09-09 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Low
T052 | IT | Update Stock DB | John | IT | 2025-09-10 | 2025-09-17 | 2025-09-20 | Delayed | 3 | Low
T053 | Approvals | Monthly Report | Sarah | Ops | 2025-09-18 | 2025-09-24 | 2025-09-25 | Delayed | 1 | Medium
T054 | Procurement | System Audit | Sarah | Ops | 2025-09-15 | 2025-09-20 | 2025-09-20 | On-Time | 0 | Low
T055 | Reporting | Order Processing | Sarah | Ops | 2025-09-08 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Medium
T056 | Approvals | Policy Review | Sarah | Ops | 2025-09-05 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T057 | Procurement | Order Processing | John | IT | 2025-09-04 | 2025-09-10 | 2025-09-09 | On-Time | -1 | Low
T058 | Approvals | Update Stock DB | David | IT | 2025-09-05 | 2025-09-11 | 2025-09-11 | On-Time | 0 | High
T059 | Approvals | Server Patch | John | IT | 2025-09-20 | 2025-09-26 | 2025-09-25 | On-Time | -1 | Medium
T060 | Procurement | Policy Review | John | IT | 2025-09-16 | 2025-09-23 | 2025-09-22 | On-Time | -1 | Low
T061 | Inventory | Sprint Update | David | IT | 2025-09-10 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Medium
T062 | Inventory | Vendor Request | Sarah | Ops | 2025-09-06 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T063 | IT | Update Stock DB | John | IT | 2025-09-12 | 2025-09-17 | 2025-09-19 | Delayed | 2 | High
T064 | Reporting | System Audit | Sarah | Ops | 2025-09-19 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T065 | Inventory | Order Processing | Sarah | Ops | 2025-09-20 | 2025-09-24 | 2025-09-26 | Delayed | 2 | Low
T066 | Reporting | Sprint Update | Sarah | Ops | 2025-09-09 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Low
T067 | Inventory | Budget Approval | John | IT | 2025-09-18 | 2025-09-22 | 2025-09-21 | On-Time | -1 | Medium
T068 | IT | Order Processing | John | IT | 2025-09-14 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T069 | Reporting | Policy Review | Sarah | Ops | 2025-09-04 | 2025-09-08 | 2025-09-10 | Delayed | 2 | Low
T070 | IT | Order Processing | John | IT | 2025-09-10 | 2025-09-13 | 2025-09-15 | Delayed | 2 | Medium
T071 | Inventory | Order Processing | David | IT | 2025-09-02 | 2025-09-09 | 2025-09-11 | Delayed | 2 | Medium
T072 | Reporting | Order Processing | John | IT | 2025-09-08 | 2025-09-12 | 2025-09-15 | Delayed | 3 | Medium
T073 | Reporting | Vendor Request | David | IT | 2025-09-02 | 2025-09-07 | 2025-09-09 | Delayed | 2 | High
T074 | Procurement | Data Backup | David | IT | 2025-09-05 | 2025-09-08 | 2025-09-09 | Delayed | 1 | Medium
T075 | Approvals | Monthly Report | Priya | Finance | 2025-09-05 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Low
T076 | Procurement | Server Patch | Priya | Finance | 2025-09-09 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Low
T077 | IT | Vendor Request | Sarah | Ops | 2025-09-03 | 2025-09-07 | 2025-09-07 | On-Time | 0 | Low
T078 | Approvals | System Audit | John | IT | 2025-09-03 | 2025-09-09 | 2025-09-08 | On-Time | -1 | Medium
T079 | Procurement | Vendor Request | Sarah | Ops | 2025-09-12 | 2025-09-17 | 2025-09-20 | Delayed | 3 | Medium
T080 | IT | Vendor Request | David | IT | 2025-09-08 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Low
T081 | Procurement | Data Backup | Nisha | Procurement | 2025-09-08 | 2025-09-11 | 2025-09-13 | Delayed | 2 | Low
T082 | IT | Policy Review | Alex | Ops | 2025-09-05 | 2025-09-08 | 2025-09-07 | On-Time | -1 | Medium
T083 | Approvals | Vendor Request | Alex | Ops | 2025-09-08 | 2025-09-15 | 2025-09-15 | On-Time | 0 | Medium
T084 | Approvals | Data Backup | David | IT | 2025-09-18 | 2025-09-24 | 2025-09-27 | Delayed | 3 | Low
T085 | Reporting | Policy Review | David | IT | 2025-09-04 | 2025-09-10 | 2025-09-13 | Delayed | 3 | Medium
T086 | IT | Update Stock DB | David | IT | 2025-09-12 | 2025-09-16 | 2025-09-18 | Delayed | 2 | Medium
T087 | Reporting | Data Backup | Alex | Ops | 2025-09-12 | 2025-09-19 | 2025-09-20 | Delayed | 1 | High
T088 | Approvals | Server Patch | Priya | Finance | 2025-09-04 | 2025-09-10 | 2025-09-09 | On-Time | -1 | Low
T089 | Reporting | Order Processing | Alex | Ops | 2025-09-02 | 2025-09-07 | 2025-09-07 | On-Time | 0 | High
T090 | Procurement | Sprint Update | Alex | Ops | 2025-09-18 | 2025-09-22 | 2025-09-25 | Delayed | 3 | High
T091 | Reporting | Data Backup | Priya | Finance | 2025-09-20 | 2025-09-23 | 2025-09-24 | Delayed | 1 | High
T092 | Reporting | System Audit | John | IT | 2025-09-06 | 2025-09-09 | 2025-09-08 | On-Time | -1 | High
T093 | Inventory | Data Backup | Priya | Finance | 2025-09-19 | 2025-09-24 | 2025-09-23 | On-Time | -1 | High
T094 | IT | Update Stock DB | Priya | Finance | 2025-09-14 | 2025-09-21 | 2025-09-20 | On-Time | -1 | Low
T095 | Inventory | Budget Approval | Sarah | Ops | 2025-09-12 | 2025-09-19 | 2025-09-22 | Delayed | 3 | High
T096 | Approvals | System Audit | Priya | Finance | 2025-09-20 | 2025-09-23 | 2025-09-26 | Delayed | 3 | Medium
T097 | Approvals | Update Stock DB | Alex | Ops | 2025-09-16 | 2025-09-22 | 2025-09-24 | Delayed | 2 | Low
T098 | Inventory | Budget Approval | David | IT | 2025-09-15 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Medium
T099 | Procurement | Monthly Report | Alex | Ops | 2025-09-05 | 2025-09-10 | 2025-09-13 | Delayed | 3 | Low
T100 | Procurement | System Audit | David | IT | 2025-09-11 | 2025-09-17 | 2025-09-20 | Delayed | 3 | Low
T101 | IT | Budget Approval | Nisha | Procurement | 2025-09-20 | 2025-09-26 | 2025-09-25 | On-Time | -1 | Low
T102 | Inventory | System Audit | David | IT | 2025-09-07 | 2025-09-13 | 2025-09-15 | Delayed | 2 | High
T103 | Approvals | Data Backup | Sarah | Ops | 2025-09-13 | 2025-09-19 | 2025-09-18 | On-Time | -1 | Medium
T104 | Approvals | Data Backup | David | IT | 2025-09-09 | 2025-09-14 | 2025-09-14 | On-Time | 0 | Low
T105 | Approvals | Vendor Request | Alex | Ops | 2025-09-03 | 2025-09-06 | 2025-09-08 | Delayed | 2 | High
T106 | IT | Monthly Report | Nisha | Procurement | 2025-09-02 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Low
T107 | IT | Vendor Request | Sarah | Ops | 2025-09-12 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Medium
T108 | Procurement | Server Patch | John | IT | 2025-09-04 | 2025-09-11 | 2025-09-14 | Delayed | 3 | High
T109 | Reporting | Budget Approval | Priya | Finance | 2025-09-04 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Medium
T110 | Inventory | Server Patch | Nisha | Procurement | 2025-09-08 | 2025-09-14 | 2025-09-17 | Delayed | 3 | Low
T111 | Procurement | System Audit | Alex | Ops | 2025-09-20 | 2025-09-25 | 2025-09-24 | On-Time | -1 | High
T112 | IT | Server Patch | John | IT | 2025-09-12 | 2025-09-15 | 2025-09-15 | On-Time | 0 | High
T113 | Procurement | Policy Review | Alex | Ops | 2025-09-05 | 2025-09-08 | 2025-09-07 | On-Time | -1 | Low
T114 | Procurement | Sprint Update | Sarah | Ops | 2025-09-14 | 2025-09-20 | 2025-09-21 | Delayed | 1 | High
T115 | IT | Server Patch | David | IT | 2025-09-11 | 2025-09-18 | 2025-09-21 | Delayed | 3 | High
T116 | Inventory | Monthly Report | Priya | Finance | 2025-09-20 | 2025-09-23 | 2025-09-22 | On-Time | -1 | Medium
T117 | Approvals | Policy Review | Sarah | Ops | 2025-09-20 | 2025-09-26 | 2025-09-28 | Delayed | 2 | Medium
T118 | Reporting | System Audit | Alex | Ops | 2025-09-12 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Medium
T119 | Procurement | Budget Approval | Nisha | Procurement | 2025-09-10 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Medium
T120 | Procurement | Update Stock DB | Alex | Ops | 2025-09-07 | 2025-09-12 | 2025-09-12 | On-Time | 0 | High
T121 | IT | Server Patch | John | IT | 2025-09-04 | 2025-09-07 | 2025-09-09 | Delayed | 2 | Low
T122 | Approvals | Monthly Report | Priya | Finance | 2025-09-13 | 2025-09-20 | 2025-09-20 | On-Time | 0 | Low
T123 | Procurement | Data Backup | Alex | Ops | 2025-09-13 | 2025-09-16 | 2025-09-18 | Delayed | 2 | High
T124 | Approvals | Vendor Request | John | IT | 2025-09-19 | 2025-09-25 | 2025-09-28 | Delayed | 3 | Medium
T125 | Approvals | Server Patch | Alex | Ops | 2025-09-13 | 2025-09-16 | 2025-09-17 | Delayed | 1 | High
T126 | Procurement | Budget Approval | David | IT | 2025-09-12 | 2025-09-15 | 2025-09-17 | Delayed | 2 | High
T127 | Reporting | Policy Review | Nisha | Procurement | 2025-09-13 | 2025-09-20 | 2025-09-19 | On-Time | -1 | Medium
T128 | IT | Data Backup | Priya | Finance | 2025-09-11 | 2025-09-15 | 2025-09-14 | On-Time | -1 | Low
T129 | Inventory | System Audit | Nisha | Procurement | 2025-09-07 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Low
T130 | Reporting | Sprint Update | Alex | Ops | 2025-09-05 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T131 | Procurement | Monthly Report | David | IT | 2025-09-03 | 2025-09-07 | 2025-09-09 | Delayed | 2 | Medium
T132 | Procurement | Order Processing | Sarah | Ops | 2025-09-19 | 2025-09-26 | 2025-09-27 | Delayed | 1 | Low
T133 | IT | Monthly Report | Sarah | Ops | 2025-09-03 | 2025-09-09 | 2025-09-11 | Delayed | 2 | Low
T134 | IT | Server Patch | Nisha | Procurement | 2025-09-02 | 2025-09-07 | 2025-09-10 | Delayed | 3 | High
T135 | IT | Budget Approval | Sarah | Ops | 2025-09-02 | 2025-09-05 | 2025-09-06 | Delayed | 1 | Medium
T136 | Inventory | Vendor Request | Nisha | Procurement | 2025-09-20 | 2025-09-27 | 2025-09-29 | Delayed | 2 | Medium
T137 | Procurement | System Audit | David | IT | 2025-09-02 | 2025-09-08 | 2025-09-11 | Delayed | 3 | Low
T138 | Reporting | Data Backup | Nisha | Procurement | 2025-09-16 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T139 | Approvals | Vendor Request | John | IT | 2025-09-03 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T140 | Reporting | Budget Approval | Sarah | Ops | 2025-09-17 | 2025-09-24 | 2025-09-27 | Delayed | 3 | High
T141 | IT | Data Backup | John | IT | 2025-09-13 | 2025-09-19 | 2025-09-20 | Delayed | 1 | Low
T142 | Procurement | Update Stock DB | David | IT | 2025-09-11 | 2025-09-14 | 2025-09-15 | Delayed | 1 | High
T143 | Procurement | Policy Review | John | IT | 2025-09-09 | 2025-09-16 | 2025-09-16 | On-Time | 0 | Medium
T144 | Inventory | Order Processing | David | IT | 2025-09-05 | 2025-09-10 | 2025-09-11 | Delayed | 1 | Low
T145 | Approvals | Monthly Report | Nisha | Procurement | 2025-09-03 | 2025-09-08 | 2025-09-11 | Delayed | 3 | Medium
T146 | IT | Monthly Report | David | IT | 2025-09-17 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Low
T147 | IT | Update Stock DB | John | IT | 2025-09-10 | 2025-09-14 | 2025-09-14 | On-Time | 0 | Medium
T148 | Approvals | Sprint Update | Priya | Finance | 2025-09-05 | 2025-09-09 | 2025-09-08 | On-Time | -1 | Medium
T149 | Inventory | System Audit | Nisha | Procurement | 2025-09-17 | 2025-09-20 | 2025-09-21 | Delayed | 1 | Low
T150 | Reporting | Order Processing | Sarah | Ops | 2025-09-05 | 2025-09-09 | 2025-09-09 | On-Time | 0 | Low
T151 | Procurement | Monthly Report | David | IT | 2025-09-15 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Medium
T152 | Reporting | Budget Approval | Nisha | Procurement | 2025-09-10 | 2025-09-16 | 2025-09-16 | On-Time | 0 | Low
T153 | Reporting | Server Patch | Sarah | Ops | 2025-09-07 | 2025-09-12 | 2025-09-15 | Delayed | 3 | Medium
T154 | Approvals | Server Patch | Sarah | Ops | 2025-09-17 | 2025-09-24 | 2025-09-26 | Delayed | 2 | High
T155 | Reporting | Order Processing | Priya | Finance | 2025-09-09 | 2025-09-12 | 2025-09-14 | Delayed | 2 | Medium
T156 | Procurement | Vendor Request | David | IT | 2025-09-17 | 2025-09-20 | 2025-09-21 | Delayed | 1 | High
T157 | Reporting | Server Patch | Sarah | Ops | 2025-09-17 | 2025-09-21 | 2025-09-23 | Delayed | 2 | High
T158 | Reporting | Budget Approval | John | IT | 2025-09-01 | 2025-09-07 | 2025-09-06 | On-Time | -1 | Medium
T159 | Procurement | Data Backup | Priya | Finance | 2025-09-13 | 2025-09-16 | 2025-09-17 | Delayed | 1 | High
T160 | Inventory | Data Backup | Alex | Ops | 2025-09-11 | 2025-09-15 | 2025-09-15 | On-Time | 0 | High
T161 | IT | Budget Approval | David | IT | 2025-09-05 | 2025-09-11 | 2025-09-13 | Delayed | 2 | Low
T162 | Inventory | Vendor Request | Alex | Ops | 2025-09-09 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Low
T163 | Procurement | System Audit | Sarah | Ops | 2025-09-04 | 2025-09-09 | 2025-09-09 | On-Time | 0 | Medium
T164 | Inventory | Update Stock DB | Priya | Finance | 2025-09-14 | 2025-09-21 | 2025-09-23 | Delayed | 2 | High
T165 | Inventory | Budget Approval | Nisha | Procurement | 2025-09-18 | 2025-09-21 | 2025-09-24 | Delayed | 3 | Low
T166 | Reporting | Monthly Report | John | IT | 2025-09-14 | 2025-09-17 | 2025-09-20 | Delayed | 3 | Medium
T167 | Reporting | Order Processing | Sarah | Ops | 2025-09-06 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Medium
T168 | Inventory | System Audit | Nisha | Procurement | 2025-09-17 | 2025-09-24 | 2025-09-27 | Delayed | 3 | High
T169 | Approvals | Budget Approval | Alex | Ops | 2025-09-13 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Low
T170 | Inventory | Data Backup | Alex | Ops | 2025-09-12 | 2025-09-16 | 2025-09-15 | On-Time | -1 | Low
T171 | IT | Monthly Report | Alex | Ops | 2025-09-12 | 2025-09-19 | 2025-09-20 | Delayed | 1 | Low
T172 | Reporting | Budget Approval | David | IT | 2025-09-16 | 2025-09-20 | 2025-09-20 | On-Time | 0 | High
T173 | Approvals | Update Stock DB | John | IT | 2025-09-07 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T174 | IT | Server Patch | Nisha | Procurement | 2025-09-13 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Medium
T175 | Inventory | Sprint Update | John | IT | 2025-09-12 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Medium
T176 | Inventory | Data Backup | Sarah | Ops | 2025-09-13 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T177 | Reporting | Budget Approval | David | IT | 2025-09-16 | 2025-09-21 | 2025-09-24 | Delayed | 3 | Medium
T178 | Inventory | Policy Review | Alex | Ops | 2025-09-14 | 2025-09-21 | 2025-09-21 | On-Time | 0 | Low
T179 | IT | Data Backup | Alex | Ops | 2025-09-03 | 2025-09-08 | 2025-09-09 | Delayed | 1 | Medium
T180 | Approvals | Order Processing | David | IT | 2025-09-14 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Medium
T181 | Approvals | Update Stock DB | David | IT | 2025-09-12 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T182 | Inventory | Vendor Request | David | IT | 2025-09-13 | 2025-09-18 | 2025-09-21 | Delayed | 3 | Low
T183 | Reporting | Update Stock DB | Priya | Finance | 2025-09-20 | 2025-09-26 | 2025-09-25 | On-Time | -1 | High
T184 | Inventory | Sprint Update | David | IT | 2025-09-12 | 2025-09-17 | 2025-09-19 | Delayed | 2 | Low
T185 | Inventory | Order Processing | Priya | Finance | 2025-09-15 | 2025-09-20 | 2025-09-21 | Delayed | 1 | Medium
T186 | Inventory | Order Processing | Priya | Finance | 2025-09-17 | 2025-09-22 | 2025-09-24 | Delayed | 2 | Medium
T187 | IT | Sprint Update | Alex | Ops | 2025-09-01 | 2025-09-05 | 2025-09-07 | Delayed | 2 | Low
T188 | Approvals | System Audit | Alex | Ops | 2025-09-09 | 2025-09-14 | 2025-09-16 | Delayed | 2 | High
T189 | Procurement | Server Patch | David | IT | 2025-09-16 | 2025-09-20 | 2025-09-19 | On-Time | -1 | High
T190 | Inventory | Budget Approval | Priya | Finance | 2025-09-15 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Low
T191 | IT | Vendor Request | Nisha | Procurement | 2025-09-18 | 2025-09-23 | 2025-09-24 | Delayed | 1 | High
T192 | Reporting | Data Backup | Nisha | Procurement | 2025-09-08 | 2025-09-11 | 2025-09-11 | On-Time | 0 | High
T193 | Reporting | Budget Approval | Alex | Ops | 2025-09-12 | 2025-09-19 | 2025-09-22 | Delayed | 3 | Medium
T194 | Approvals | System Audit | Priya | Finance | 2025-09-20 | 2025-09-23 | 2025-09-22 | On-Time | -1 | Medium
T195 | Approvals | Budget Approval | Nisha | Procurement | 2025-09-14 | 2025-09-20 | 2025-09-23 | Delayed | 3 | High
T196 | Reporting | Data Backup | David | IT | 2025-09-03 | 2025-09-09 | 2025-09-11 | Delayed | 2 | Low
T197 | Procurement | Data Backup | Priya | Finance | 2025-09-18 | 2025-09-25 | 2025-09-25 | On-Time | 0 | High
T198 | Approvals | System Audit | Alex | Ops | 2025-09-04 | 2025-09-11 | 2025-09-11 | On-Time | 0 | Medium
T199 | Reporting | Monthly Report | John | IT | 2025-09-08 | 2025-09-13 | 2025-09-16 | Delayed | 3 | Medium
T200 | Inventory | Server Patch | Priya | Finance | 2025-09-18 | 2025-09-23 | 2025-09-23 | On-Time | 0 | Low
T201 | IT | Order Processing | Nisha | Procurement | 2025-09-03 | 2025-09-10 | 2025-09-10 | On-Time | 0 | Low
T202 | Procurement | Monthly Report | Priya | Finance | 2025-09-20 | 2025-09-27 | 2025-09-28 | Delayed | 1 | Low
T203 | Inventory | Update Stock DB | Alex | Ops | 2025-09-02 | 2025-09-09 | 2025-09-10 | Delayed | 1 | Low
T204 | Reporting | Order Processing | Sarah | Ops | 2025-09-20 | 2025-09-23 | 2025-09-25 | Delayed | 2 | Low
T205 | Procurement | Server Patch | David | IT | 2025-09-10 | 2025-09-16 | 2025-09-16 | On-Time | 0 | Low
T206 | Approvals | Server Patch | Sarah | Ops | 2025-09-03 | 2025-09-06 | 2025-09-06 | On-Time | 0 | Medium
T207 | Approvals | Budget Approval | Sarah | Ops | 2025-09-07 | 2025-09-12 | 2025-09-15 | Delayed | 3 | High
T208 | IT | Data Backup | David | IT | 2025-09-12 | 2025-09-18 | 2025-09-18 | On-Time | 0 | Medium
T209 | Procurement | System Audit | Alex | Ops | 2025-09-11 | 2025-09-15 | 2025-09-17 | Delayed | 2 | High
T210 | IT | Budget Approval | Priya | Finance | 2025-09-05 | 2025-09-08 | 2025-09-07 | On-Time | -1 | Medium
T211 | Approvals | Order Processing | Sarah | Ops | 2025-09-08 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Low
T212 | IT | Sprint Update | Priya | Finance | 2025-09-16 | 2025-09-23 | 2025-09-25 | Delayed | 2 | Medium
T213 | IT | Budget Approval | Alex | Ops | 2025-09-03 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Medium
T214 | Reporting | Sprint Update | Nisha | Procurement | 2025-09-12 | 2025-09-15 | 2025-09-14 | On-Time | -1 | Medium
T215 | Approvals | Order Processing | David | IT | 2025-09-16 | 2025-09-21 | 2025-09-24 | Delayed | 3 | High
T216 | Inventory | Policy Review | Priya | Finance | 2025-09-09 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Medium
T217 | Inventory | Policy Review | Alex | Ops | 2025-09-19 | 2025-09-26 | 2025-09-26 | On-Time | 0 | Medium
T218 | Procurement | Server Patch | Alex | Ops | 2025-09-13 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Low
T219 | IT | Order Processing | David | IT | 2025-09-20 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T220 | Approvals | Data Backup | John | IT | 2025-09-18 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T221 | Procurement | System Audit | Sarah | Ops | 2025-09-17 | 2025-09-20 | 2025-09-19 | On-Time | -1 | High
T222 | Reporting | Data Backup | Sarah | Ops | 2025-09-17 | 2025-09-23 | 2025-09-23 | On-Time | 0 | Low
T223 | Procurement | Monthly Report | John | IT | 2025-09-20 | 2025-09-25 | 2025-09-25 | On-Time | 0 | Medium
T224 | Procurement | Server Patch | Nisha | Procurement | 2025-09-11 | 2025-09-18 | 2025-09-21 | Delayed | 3 | Low
T225 | Approvals | Order Processing | John | IT | 2025-09-16 | 2025-09-19 | 2025-09-20 | Delayed | 1 | Medium
T226 | Inventory | Policy Review | Nisha | Procurement | 2025-09-10 | 2025-09-13 | 2025-09-16 | Delayed | 3 | Medium
T227 | IT | Order Processing | Nisha | Procurement | 2025-09-08 | 2025-09-11 | 2025-09-14 | Delayed | 3 | Medium
T228 | Reporting | System Audit | David | IT | 2025-09-20 | 2025-09-26 | 2025-09-26 | On-Time | 0 | Low
T229 | Reporting | Update Stock DB | Nisha | Procurement | 2025-09-04 | 2025-09-08 | 2025-09-07 | On-Time | -1 | Medium
T230 | IT | Policy Review | Priya | Finance | 2025-09-14 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Low
T231 | Procurement | Budget Approval | David | IT | 2025-09-02 | 2025-09-06 | 2025-09-09 | Delayed | 3 | High
T232 | Procurement | Data Backup | David | IT | 2025-09-16 | 2025-09-23 | 2025-09-25 | Delayed | 2 | Medium
T233 | Reporting | Budget Approval | Nisha | Procurement | 2025-09-11 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Low
T234 | IT | Order Processing | Sarah | Ops | 2025-09-07 | 2025-09-11 | 2025-09-12 | Delayed | 1 | Low
T235 | IT | Sprint Update | John | IT | 2025-09-10 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Medium
T236 | Approvals | Data Backup | Nisha | Procurement | 2025-09-09 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Low
T237 | Procurement | Policy Review | Sarah | Ops | 2025-09-12 | 2025-09-16 | 2025-09-17 | Delayed | 1 | High
T238 | IT | Vendor Request | John | IT | 2025-09-15 | 2025-09-20 | 2025-09-22 | Delayed | 2 | High
T239 | Reporting | System Audit | John | IT | 2025-09-18 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T240 | Procurement | Order Processing | Priya | Finance | 2025-09-08 | 2025-09-11 | 2025-09-14 | Delayed | 3 | High
T241 | Reporting | Update Stock DB | Alex | Ops | 2025-09-14 | 2025-09-19 | 2025-09-21 | Delayed | 2 | High
T242 | Reporting | Update Stock DB | Nisha | Procurement | 2025-09-06 | 2025-09-12 | 2025-09-14 | Delayed | 2 | Medium
T243 | Reporting | Server Patch | John | IT | 2025-09-10 | 2025-09-13 | 2025-09-12 | On-Time | -1 | Low
T244 | Procurement | Sprint Update | Nisha | Procurement | 2025-09-02 | 2025-09-06 | 2025-09-08 | Delayed | 2 | High
T245 | Inventory | Policy Review | Sarah | Ops | 2025-09-06 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T246 | IT | Order Processing | Nisha | Procurement | 2025-09-04 | 2025-09-09 | 2025-09-10 | Delayed | 1 | Medium
T247 | Procurement | System Audit | Sarah | Ops | 2025-09-05 | 2025-09-12 | 2025-09-14 | Delayed | 2 | Medium
T248 | Reporting | Vendor Request | John | IT | 2025-09-06 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Low
T249 | Reporting | Update Stock DB | David | IT | 2025-09-11 | 2025-09-16 | 2025-09-19 | Delayed | 3 | Low
T250 | Reporting | Monthly Report | Nisha | Procurement | 2025-09-13 | 2025-09-19 | 2025-09-22 | Delayed | 3 | Medium
T251 | Inventory | Policy Review | David | IT | 2025-09-04 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Medium
T252 | IT | Sprint Update | Alex | Ops | 2025-09-09 | 2025-09-15 | 2025-09-15 | On-Time | 0 | Medium
T253 | IT | Data Backup | John | IT | 2025-09-19 | 2025-09-26 | 2025-09-25 | On-Time | -1 | Medium
T254 | IT | Sprint Update | Alex | Ops | 2025-09-04 | 2025-09-10 | 2025-09-11 | Delayed | 1 | High
T255 | Approvals | System Audit | David | IT | 2025-09-10 | 2025-09-13 | 2025-09-14 | Delayed | 1 | Medium
T256 | Procurement | Sprint Update | Priya | Finance | 2025-09-05 | 2025-09-11 | 2025-09-11 | On-Time | 0 | Medium
T257 | Procurement | Data Backup | Sarah | Ops | 2025-09-18 | 2025-09-24 | 2025-09-27 | Delayed | 3 | Low
T258 | Reporting | Sprint Update | David | IT | 2025-09-20 | 2025-09-23 | 2025-09-26 | Delayed | 3 | Medium
T259 | Procurement | Data Backup | Alex | Ops | 2025-09-19 | 2025-09-22 | 2025-09-21 | On-Time | -1 | Low
T260 | Procurement | Sprint Update | Nisha | Procurement | 2025-09-18 | 2025-09-22 | 2025-09-22 | On-Time | 0 | Medium
T261 | Procurement | Budget Approval | Alex | Ops | 2025-09-07 | 2025-09-14 | 2025-09-16 | Delayed | 2 | High
T262 | Procurement | Budget Approval | Alex | Ops | 2025-09-15 | 2025-09-19 | 2025-09-22 | Delayed | 3 | Medium
T263 | Approvals | Order Processing | Alex | Ops | 2025-09-18 | 2025-09-24 | 2025-09-25 | Delayed | 1 | Low
T264 | Inventory | Policy Review | John | IT | 2025-09-01 | 2025-09-05 | 2025-09-08 | Delayed | 3 | High
T265 | Inventory | Policy Review | John | IT | 2025-09-03 | 2025-09-10 | 2025-09-09 | On-Time | -1 | High
T266 | Approvals | Update Stock DB | John | IT | 2025-09-14 | 2025-09-18 | 2025-09-18 | On-Time | 0 | Low
T267 | Approvals | Data Backup | Sarah | Ops | 2025-09-15 | 2025-09-21 | 2025-09-23 | Delayed | 2 | High
T268 | Procurement | Monthly Report | David | IT | 2025-09-12 | 2025-09-15 | 2025-09-15 | On-Time | 0 | Low
T269 | Approvals | System Audit | Priya | Finance | 2025-09-08 | 2025-09-11 | 2025-09-10 | On-Time | -1 | Medium
T270 | Approvals | System Audit | Sarah | Ops | 2025-09-18 | 2025-09-24 | 2025-09-24 | On-Time | 0 | High
T271 | Approvals | Data Backup | Priya | Finance | 2025-09-09 | 2025-09-13 | 2025-09-12 | On-Time | -1 | High
T272 | Approvals | Order Processing | Alex | Ops | 2025-09-08 | 2025-09-12 | 2025-09-11 | On-Time | -1 | High
T273 | Procurement | Update Stock DB | Sarah | Ops | 2025-09-20 | 2025-09-23 | 2025-09-23 | On-Time | 0 | Low
T274 | Inventory | Policy Review | Sarah | Ops | 2025-09-08 | 2025-09-15 | 2025-09-15 | On-Time | 0 | High
T275 | Reporting | System Audit | John | IT | 2025-09-08 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Low
T276 | Procurement | Data Backup | Priya | Finance | 2025-09-10 | 2025-09-14 | 2025-09-17 | Delayed | 3 | High
T277 | Approvals | Server Patch | John | IT | 2025-09-02 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Low
T278 | Reporting | Policy Review | Nisha | Procurement | 2025-09-16 | 2025-09-19 | 2025-09-20 | Delayed | 1 | Low
T279 | Approvals | System Audit | John | IT | 2025-09-14 | 2025-09-20 | 2025-09-20 | On-Time | 0 | Medium
T280 | Approvals | Monthly Report | Nisha | Procurement | 2025-09-16 | 2025-09-20 | 2025-09-20 | On-Time | 0 | Medium
T281 | Reporting | Budget Approval | Alex | Ops | 2025-09-18 | 2025-09-24 | 2025-09-26 | Delayed | 2 | Low
T282 | Procurement | Monthly Report | Sarah | Ops | 2025-09-08 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Medium
T283 | Inventory | Budget Approval | John | IT | 2025-09-03 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T284 | IT | Policy Review | David | IT | 2025-09-20 | 2025-09-27 | 2025-09-26 | On-Time | -1 | High
T285 | Reporting | Order Processing | David | IT | 2025-09-18 | 2025-09-22 | 2025-09-24 | Delayed | 2 | High
T286 | IT | Server Patch | Alex | Ops | 2025-09-07 | 2025-09-11 | 2025-09-10 | On-Time | -1 | Low
T287 | Approvals | Sprint Update | David | IT | 2025-09-20 | 2025-09-24 | 2025-09-26 | Delayed | 2 | High
T288 | Procurement | Data Backup | John | IT | 2025-09-13 | 2025-09-19 | 2025-09-22 | Delayed | 3 | Low
T289 | IT | Server Patch | John | IT | 2025-09-12 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T290 | Inventory | Budget Approval | John | IT | 2025-09-07 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Medium
T291 | Inventory | Order Processing | Priya | Finance | 2025-09-05 | 2025-09-08 | 2025-09-09 | Delayed | 1 | Low
T292 | Procurement | Order Processing | David | IT | 2025-09-14 | 2025-09-19 | 2025-09-19 | On-Time | 0 | High
T293 | IT | Sprint Update | Sarah | Ops | 2025-09-19 | 2025-09-23 | 2025-09-25 | Delayed | 2 | Low
T294 | IT | Server Patch | Sarah | Ops | 2025-09-16 | 2025-09-22 | 2025-09-22 | On-Time | 0 | Low
T295 | IT | Monthly Report | Priya | Finance | 2025-09-18 | 2025-09-24 | 2025-09-24 | On-Time | 0 | Low
T296 | Inventory | System Audit | Alex | Ops | 2025-09-03 | 2025-09-06 | 2025-09-05 | On-Time | -1 | Medium
T297 | Reporting | Sprint Update | Alex | Ops | 2025-09-05 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Low
T298 | Approvals | Data Backup | Alex | Ops | 2025-09-20 | 2025-09-27 | 2025-09-29 | Delayed | 2 | Low
T299 | Approvals | Update Stock DB | Alex | Ops | 2025-09-18 | 2025-09-25 | 2025-09-27 | Delayed | 2 | High
T300 | Inventory | System Audit | David | IT | 2025-09-09 | 2025-09-16 | 2025-09-17 | Delayed | 1 | High
T301 | Procurement | Policy Review | Priya | Finance | 2025-09-04 | 2025-09-07 | 2025-09-10 | Delayed | 3 | High
T302 | Reporting | Sprint Update | Nisha | Procurement | 2025-09-17 | 2025-09-22 | 2025-09-23 | Delayed | 1 | Medium
T303 | Approvals | Vendor Request | John | IT | 2025-09-13 | 2025-09-19 | 2025-09-22 | Delayed | 3 | High
T304 | Reporting | Server Patch | David | IT | 2025-09-03 | 2025-09-06 | 2025-09-05 | On-Time | -1 | Medium
T305 | Approvals | Policy Review | Nisha | Procurement | 2025-09-16 | 2025-09-19 | 2025-09-18 | On-Time | -1 | Low
T306 | Reporting | Vendor Request | Sarah | Ops | 2025-09-14 | 2025-09-19 | 2025-09-22 | Delayed | 3 | High
T307 | Procurement | Update Stock DB | Priya | Finance | 2025-09-07 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Medium
T308 | Inventory | Vendor Request | David | IT | 2025-09-09 | 2025-09-16 | 2025-09-19 | Delayed | 3 | Low
T309 | Inventory | Monthly Report | John | IT | 2025-09-01 | 2025-09-05 | 2025-09-08 | Delayed | 3 | High
T310 | Approvals | Vendor Request | John | IT | 2025-09-06 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Low
T311 | Approvals | System Audit | John | IT | 2025-09-13 | 2025-09-17 | 2025-09-16 | On-Time | -1 | Low
T312 | IT | Update Stock DB | Alex | Ops | 2025-09-14 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Medium
T313 | Procurement | Order Processing | Nisha | Procurement | 2025-09-13 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Low
T314 | IT | Budget Approval | Sarah | Ops | 2025-09-08 | 2025-09-13 | 2025-09-16 | Delayed | 3 | Medium
T315 | Approvals | Monthly Report | David | IT | 2025-09-19 | 2025-09-25 | 2025-09-24 | On-Time | -1 | Low
T316 | IT | Sprint Update | David | IT | 2025-09-03 | 2025-09-06 | 2025-09-07 | Delayed | 1 | High
T317 | Approvals | Monthly Report | David | IT | 2025-09-13 | 2025-09-18 | 2025-09-19 | Delayed | 1 | High
T318 | Inventory | Update Stock DB | John | IT | 2025-09-15 | 2025-09-20 | 2025-09-21 | Delayed | 1 | High
T319 | Reporting | Vendor Request | Priya | Finance | 2025-09-14 | 2025-09-20 | 2025-09-23 | Delayed | 3 | Low
T320 | Procurement | Policy Review | Alex | Ops | 2025-09-01 | 2025-09-04 | 2025-09-05 | Delayed | 1 | Low
T321 | Inventory | Order Processing | Nisha | Procurement | 2025-09-11 | 2025-09-17 | 2025-09-16 | On-Time | -1 | Medium
T322 | Approvals | Policy Review | Alex | Ops | 2025-09-18 | 2025-09-22 | 2025-09-25 | Delayed | 3 | Low
T323 | Reporting | Policy Review | Priya | Finance | 2025-09-05 | 2025-09-10 | 2025-09-11 | Delayed | 1 | Medium
T324 | Approvals | Monthly Report | Alex | Ops | 2025-09-06 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Medium
T325 | IT | Budget Approval | Alex | Ops | 2025-09-12 | 2025-09-17 | 2025-09-17 | On-Time | 0 | Low
T326 | Approvals | Order Processing | Nisha | Procurement | 2025-09-07 | 2025-09-13 | 2025-09-12 | On-Time | -1 | High
T327 | IT | Update Stock DB | Sarah | Ops | 2025-09-11 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Medium
T328 | Approvals | Data Backup | Sarah | Ops | 2025-09-20 | 2025-09-24 | 2025-09-25 | Delayed | 1 | Medium
T329 | Procurement | Sprint Update | Sarah | Ops | 2025-09-11 | 2025-09-15 | 2025-09-17 | Delayed | 2 | Medium
T330 | IT | Budget Approval | Nisha | Procurement | 2025-09-08 | 2025-09-13 | 2025-09-15 | Delayed | 2 | Medium
T331 | Approvals | Data Backup | Alex | Ops | 2025-09-19 | 2025-09-23 | 2025-09-26 | Delayed | 3 | Low
T332 | Reporting | System Audit | Alex | Ops | 2025-09-15 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Medium
T333 | Inventory | Policy Review | David | IT | 2025-09-16 | 2025-09-20 | 2025-09-21 | Delayed | 1 | High
T334 | IT | Monthly Report | David | IT | 2025-09-14 | 2025-09-20 | 2025-09-19 | On-Time | -1 | Medium
T335 | Procurement | Budget Approval | Nisha | Procurement | 2025-09-13 | 2025-09-20 | 2025-09-23 | Delayed | 3 | Low
T336 | Approvals | System Audit | Alex | Ops | 2025-09-12 | 2025-09-19 | 2025-09-22 | Delayed | 3 | Low
T337 | Inventory | Vendor Request | Priya | Finance | 2025-09-12 | 2025-09-16 | 2025-09-19 | Delayed | 3 | High
T338 | Procurement | Policy Review | John | IT | 2025-09-14 | 2025-09-17 | 2025-09-16 | On-Time | -1 | High
T339 | IT | Sprint Update | Nisha | Procurement | 2025-09-17 | 2025-09-24 | 2025-09-27 | Delayed | 3 | Low
T340 | Procurement | Sprint Update | Sarah | Ops | 2025-09-12 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Low
T341 | Procurement | System Audit | Priya | Finance | 2025-09-12 | 2025-09-15 | 2025-09-17 | Delayed | 2 | High
T342 | IT | Policy Review | Alex | Ops | 2025-09-04 | 2025-09-08 | 2025-09-09 | Delayed | 1 | Medium
T343 | IT | Budget Approval | Priya | Finance | 2025-09-17 | 2025-09-23 | 2025-09-24 | Delayed | 1 | Medium
T344 | Inventory | Budget Approval | David | IT | 2025-09-15 | 2025-09-20 | 2025-09-19 | On-Time | -1 | Medium
T345 | Inventory | Vendor Request | Alex | Ops | 2025-09-11 | 2025-09-14 | 2025-09-14 | On-Time | 0 | Low
T346 | Reporting | System Audit | Priya | Finance | 2025-09-18 | 2025-09-22 | 2025-09-23 | Delayed | 1 | Low
T347 | Approvals | Budget Approval | Priya | Finance | 2025-09-13 | 2025-09-17 | 2025-09-17 | On-Time | 0 | Low
T348 | Approvals | Policy Review | Alex | Ops | 2025-09-20 | 2025-09-24 | 2025-09-26 | Delayed | 2 | Low
T349 | Approvals | Policy Review | Alex | Ops | 2025-09-07 | 2025-09-11 | 2025-09-12 | Delayed | 1 | Low
T350 | Inventory | Order Processing | Alex | Ops | 2025-09-18 | 2025-09-22 | 2025-09-23 | Delayed | 1 | Medium
T351 | Reporting | Budget Approval | Alex | Ops | 2025-09-09 | 2025-09-15 | 2025-09-18 | Delayed | 3 | Low
T352 | IT | Order Processing | Sarah | Ops | 2025-09-20 | 2025-09-26 | 2025-09-29 | Delayed | 3 | High
T353 | IT | Data Backup | Sarah | Ops | 2025-09-20 | 2025-09-24 | 2025-09-25 | Delayed | 1 | Low
T354 | Procurement | Vendor Request | David | IT | 2025-09-05 | 2025-09-10 | 2025-09-09 | On-Time | -1 | High
T355 | IT | Vendor Request | Priya | Finance | 2025-09-12 | 2025-09-16 | 2025-09-19 | Delayed | 3 | Medium
T356 | Approvals | Order Processing | Priya | Finance | 2025-09-19 | 2025-09-25 | 2025-09-27 | Delayed | 2 | High
T357 | Approvals | System Audit | David | IT | 2025-09-06 | 2025-09-13 | 2025-09-13 | On-Time | 0 | Medium
T358 | IT | Monthly Report | Priya | Finance | 2025-09-11 | 2025-09-17 | 2025-09-20 | Delayed | 3 | High
T359 | IT | Update Stock DB | Sarah | Ops | 2025-09-05 | 2025-09-09 | 2025-09-11 | Delayed | 2 | Low
T360 | Procurement | Budget Approval | Sarah | Ops | 2025-09-16 | 2025-09-22 | 2025-09-24 | Delayed | 2 | Medium
T361 | Reporting | Vendor Request | Nisha | Procurement | 2025-09-01 | 2025-09-05 | 2025-09-06 | Delayed | 1 | High
T362 | IT | Sprint Update | Nisha | Procurement | 2025-09-10 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Low
T363 | Approvals | System Audit | Nisha | Procurement | 2025-09-04 | 2025-09-11 | 2025-09-10 | On-Time | -1 | Medium
T364 | Procurement | Data Backup | Nisha | Procurement | 2025-09-02 | 2025-09-08 | 2025-09-11 | Delayed | 3 | High
T365 | Approvals | Vendor Request | David | IT | 2025-09-08 | 2025-09-13 | 2025-09-12 | On-Time | -1 | Medium
T366 | IT | Data Backup | Alex | Ops | 2025-09-15 | 2025-09-18 | 2025-09-18 | On-Time | 0 | High
T367 | Procurement | Data Backup | David | IT | 2025-09-20 | 2025-09-26 | 2025-09-26 | On-Time | 0 | Low
T368 | Reporting | Sprint Update | Priya | Finance | 2025-09-02 | 2025-09-09 | 2025-09-10 | Delayed | 1 | Low
T369 | IT | Order Processing | Nisha | Procurement | 2025-09-06 | 2025-09-11 | 2025-09-12 | Delayed | 1 | Medium
T370 | Procurement | Server Patch | Nisha | Procurement | 2025-09-04 | 2025-09-08 | 2025-09-10 | Delayed | 2 | High
T371 | IT | Monthly Report | David | IT | 2025-09-05 | 2025-09-09 | 2025-09-09 | On-Time | 0 | Low
T372 | IT | Sprint Update | David | IT | 2025-09-13 | 2025-09-19 | 2025-09-19 | On-Time | 0 | Low
T373 | IT | Policy Review | Sarah | Ops | 2025-09-15 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Medium
T374 | Procurement | Server Patch | David | IT | 2025-09-12 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Medium
T375 | Procurement | Update Stock DB | David | IT | 2025-09-03 | 2025-09-09 | 2025-09-10 | Delayed | 1 | High
T376 | Procurement | Policy Review | Priya | Finance | 2025-09-14 | 2025-09-18 | 2025-09-20 | Delayed | 2 | Medium
T377 | IT | Server Patch | John | IT | 2025-09-18 | 2025-09-25 | 2025-09-25 | On-Time | 0 | Low
T378 | Approvals | Data Backup | David | IT | 2025-09-02 | 2025-09-05 | 2025-09-04 | On-Time | -1 | Low
T379 | Approvals | Update Stock DB | Alex | Ops | 2025-09-06 | 2025-09-12 | 2025-09-14 | Delayed | 2 | High
T380 | Approvals | Sprint Update | David | IT | 2025-09-05 | 2025-09-10 | 2025-09-10 | On-Time | 0 | Medium
T381 | Inventory | Data Backup | John | IT | 2025-09-03 | 2025-09-08 | 2025-09-08 | On-Time | 0 | High
T382 | Approvals | Server Patch | David | IT | 2025-09-08 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Low
T383 | Inventory | Update Stock DB | Priya | Finance | 2025-09-16 | 2025-09-19 | 2025-09-19 | On-Time | 0 | Low
T384 | Reporting | System Audit | David | IT | 2025-09-15 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Low
T385 | IT | Vendor Request | Sarah | Ops | 2025-09-05 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T386 | Approvals | Vendor Request | David | IT | 2025-09-04 | 2025-09-07 | 2025-09-08 | Delayed | 1 | Medium
T387 | IT | Monthly Report | Sarah | Ops | 2025-09-05 | 2025-09-09 | 2025-09-08 | On-Time | -1 | Low
T388 | Procurement | Update Stock DB | Nisha | Procurement | 2025-09-06 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Low
T389 | Reporting | Monthly Report | Sarah | Ops | 2025-09-20 | 2025-09-26 | 2025-09-26 | On-Time | 0 | High
T390 | Inventory | Monthly Report | Alex | Ops | 2025-09-19 | 2025-09-25 | 2025-09-26 | Delayed | 1 | Medium
T391 | IT | Monthly Report | Priya | Finance | 2025-09-09 | 2025-09-12 | 2025-09-12 | On-Time | 0 | Low
T392 | Procurement | Order Processing | David | IT | 2025-09-20 | 2025-09-25 | 2025-09-24 | On-Time | -1 | Low
T393 | IT | Sprint Update | Nisha | Procurement | 2025-09-20 | 2025-09-27 | 2025-09-27 | On-Time | 0 | Low
T394 | Approvals | Server Patch | David | IT | 2025-09-02 | 2025-09-06 | 2025-09-08 | Delayed | 2 | Medium
T395 | Inventory | Sprint Update | Sarah | Ops | 2025-09-20 | 2025-09-23 | 2025-09-26 | Delayed | 3 | High
T396 | IT | Data Backup | Priya | Finance | 2025-09-13 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Medium
T397 | Procurement | Monthly Report | Sarah | Ops | 2025-09-03 | 2025-09-06 | 2025-09-09 | Delayed | 3 | High
T398 | Inventory | Server Patch | Priya | Finance | 2025-09-02 | 2025-09-05 | 2025-09-07 | Delayed | 2 | Low
T399 | IT | System Audit | Sarah | Ops | 2025-09-14 | 2025-09-20 | 2025-09-19 | On-Time | -1 | Low
T400 | Procurement | System Audit | Nisha | Procurement | 2025-09-05 | 2025-09-10 | 2025-09-09 | On-Time | -1 | Medium
T401 | Inventory | System Audit | Priya | Finance | 2025-09-05 | 2025-09-12 | 2025-09-13 | Delayed | 1 | Medium
T402 | Procurement | Vendor Request | John | IT | 2025-09-14 | 2025-09-18 | 2025-09-17 | On-Time | -1 | High
T403 | Inventory | Policy Review | Alex | Ops | 2025-09-15 | 2025-09-22 | 2025-09-25 | Delayed | 3 | High
T404 | IT | Monthly Report | Alex | Ops | 2025-09-01 | 2025-09-05 | 2025-09-04 | On-Time | -1 | High
T405 | Approvals | Data Backup | Nisha | Procurement | 2025-09-17 | 2025-09-22 | 2025-09-22 | On-Time | 0 | Medium
T406 | Reporting | Server Patch | David | IT | 2025-09-04 | 2025-09-07 | 2025-09-08 | Delayed | 1 | Medium
T407 | IT | System Audit | Alex | Ops | 2025-09-09 | 2025-09-16 | 2025-09-15 | On-Time | -1 | Medium
T408 | Approvals | System Audit | John | IT | 2025-09-02 | 2025-09-08 | 2025-09-11 | Delayed | 3 | High
T409 | IT | Monthly Report | John | IT | 2025-09-04 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T410 | Procurement | Update Stock DB | Alex | Ops | 2025-09-01 | 2025-09-05 | 2025-09-04 | On-Time | -1 | Medium
T411 | IT | Policy Review | Priya | Finance | 2025-09-06 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Low
T412 | Approvals | Sprint Update | John | IT | 2025-09-08 | 2025-09-14 | 2025-09-15 | Delayed | 1 | Medium
T413 | Inventory | Order Processing | John | IT | 2025-09-04 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T414 | Reporting | System Audit | Alex | Ops | 2025-09-13 | 2025-09-16 | 2025-09-18 | Delayed | 2 | Medium
T415 | IT | Data Backup | Alex | Ops | 2025-09-18 | 2025-09-24 | 2025-09-23 | On-Time | -1 | Medium
T416 | Reporting | Server Patch | Nisha | Procurement | 2025-09-10 | 2025-09-17 | 2025-09-17 | On-Time | 0 | Medium
T417 | IT | Order Processing | Sarah | Ops | 2025-09-07 | 2025-09-14 | 2025-09-14 | On-Time | 0 | High
T418 | Inventory | Policy Review | Alex | Ops | 2025-09-08 | 2025-09-15 | 2025-09-16 | Delayed | 1 | Low
T419 | Inventory | Data Backup | Alex | Ops | 2025-09-13 | 2025-09-18 | 2025-09-17 | On-Time | -1 | High
T420 | Procurement | Sprint Update | Sarah | Ops | 2025-09-16 | 2025-09-19 | 2025-09-19 | On-Time | 0 | Low
T421 | IT | Vendor Request | Alex | Ops | 2025-09-08 | 2025-09-15 | 2025-09-17 | Delayed | 2 | Low
T422 | IT | Budget Approval | David | IT | 2025-09-03 | 2025-09-10 | 2025-09-09 | On-Time | -1 | Low
T423 | Reporting | Policy Review | Alex | Ops | 2025-09-19 | 2025-09-26 | 2025-09-25 | On-Time | -1 | Medium
T424 | Reporting | Sprint Update | John | IT | 2025-09-09 | 2025-09-14 | 2025-09-16 | Delayed | 2 | Low
T425 | IT | Data Backup | Sarah | Ops | 2025-09-09 | 2025-09-13 | 2025-09-12 | On-Time | -1 | High
T426 | Reporting | Order Processing | Alex | Ops | 2025-09-05 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Medium
T427 | Approvals | Data Backup | Sarah | Ops | 2025-09-04 | 2025-09-11 | 2025-09-12 | Delayed | 1 | High
T428 | Approvals | Server Patch | Sarah | Ops | 2025-09-09 | 2025-09-12 | 2025-09-11 | On-Time | -1 | High
T429 | IT | Order Processing | Alex | Ops | 2025-09-07 | 2025-09-12 | 2025-09-12 | On-Time | 0 | High
T430 | Reporting | Data Backup | Sarah | Ops | 2025-09-17 | 2025-09-20 | 2025-09-21 | Delayed | 1 | Medium
T431 | Reporting | Update Stock DB | Sarah | Ops | 2025-09-15 | 2025-09-22 | 2025-09-25 | Delayed | 3 | High
T432 | Inventory | Budget Approval | Alex | Ops | 2025-09-05 | 2025-09-08 | 2025-09-07 | On-Time | -1 | High
T433 | Reporting | Monthly Report | Priya | Finance | 2025-09-13 | 2025-09-18 | 2025-09-17 | On-Time | -1 | Low
T434 | Procurement | Server Patch | Alex | Ops | 2025-09-01 | 2025-09-04 | 2025-09-04 | On-Time | 0 | Low
T435 | Approvals | Monthly Report | Alex | Ops | 2025-09-11 | 2025-09-14 | 2025-09-13 | On-Time | -1 | Medium
T436 | Inventory | Monthly Report | Nisha | Procurement | 2025-09-14 | 2025-09-20 | 2025-09-22 | Delayed | 2 | High
T437 | Approvals | Policy Review | Priya | Finance | 2025-09-12 | 2025-09-16 | 2025-09-16 | On-Time | 0 | Medium
T438 | IT | Budget Approval | Priya | Finance | 2025-09-02 | 2025-09-09 | 2025-09-12 | Delayed | 3 | Low
T439 | Reporting | Server Patch | Sarah | Ops | 2025-09-14 | 2025-09-21 | 2025-09-23 | Delayed | 2 | High
T440 | Inventory | Server Patch | Sarah | Ops | 2025-09-05 | 2025-09-11 | 2025-09-11 | On-Time | 0 | Low
T441 | Procurement | Sprint Update | David | IT | 2025-09-18 | 2025-09-21 | 2025-09-23 | Delayed | 2 | Low
T442 | IT | Budget Approval | Nisha | Procurement | 2025-09-16 | 2025-09-21 | 2025-09-24 | Delayed | 3 | Low
T443 | IT | Policy Review | John | IT | 2025-09-06 | 2025-09-09 | 2025-09-10 | Delayed | 1 | Low
T444 | Reporting | Update Stock DB | John | IT | 2025-09-02 | 2025-09-08 | 2025-09-11 | Delayed | 3 | Medium
T445 | Procurement | Sprint Update | Priya | Finance | 2025-09-04 | 2025-09-08 | 2025-09-08 | On-Time | 0 | Medium
T446 | Procurement | Update Stock DB | Priya | Finance | 2025-09-19 | 2025-09-25 | 2025-09-26 | Delayed | 1 | High
T447 | Reporting | Sprint Update | Nisha | Procurement | 2025-09-11 | 2025-09-16 | 2025-09-19 | Delayed | 3 | High
T448 | IT | Order Processing | Nisha | Procurement | 2025-09-05 | 2025-09-12 | 2025-09-12 | On-Time | 0 | Medium
T449 | Procurement | Server Patch | Priya | Finance | 2025-09-16 | 2025-09-19 | 2025-09-18 | On-Time | -1 | High
T450 | Reporting | Order Processing | Priya | Finance | 2025-09-01 | 2025-09-08 | 2025-09-10 | Delayed | 2 | High
T451 | IT | Order Processing | Priya | Finance | 2025-09-05 | 2025-09-10 | 2025-09-10 | On-Time | 0 | Medium
T452 | Inventory | Update Stock DB | Priya | Finance | 2025-09-19 | 2025-09-23 | 2025-09-22 | On-Time | -1 | Low
T453 | IT | Vendor Request | John | IT | 2025-09-13 | 2025-09-20 | 2025-09-19 | On-Time | -1 | Medium
T454 | IT | Data Backup | Priya | Finance | 2025-09-06 | 2025-09-12 | 2025-09-14 | Delayed | 2 | Low
T455 | IT | Monthly Report | David | IT | 2025-09-18 | 2025-09-25 | 2025-09-26 | Delayed | 1 | High
T456 | Procurement | Monthly Report | Sarah | Ops | 2025-09-10 | 2025-09-15 | 2025-09-15 | On-Time | 0 | High
T457 | Inventory | Order Processing | Sarah | Ops | 2025-09-19 | 2025-09-22 | 2025-09-22 | On-Time | 0 | Low
T458 | IT | Order Processing | Priya | Finance | 2025-09-19 | 2025-09-22 | 2025-09-24 | Delayed | 2 | High
T459 | IT | Vendor Request | Priya | Finance | 2025-09-12 | 2025-09-17 | 2025-09-17 | On-Time | 0 | Low
T460 | Inventory | Data Backup | Sarah | Ops | 2025-09-01 | 2025-09-06 | 2025-09-06 | On-Time | 0 | High
T461 | Inventory | Data Backup | John | IT | 2025-09-04 | 2025-09-07 | 2025-09-06 | On-Time | -1 | Medium
T462 | Approvals | Policy Review | Priya | Finance | 2025-09-14 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Medium
T463 | Procurement | Policy Review | Alex | Ops | 2025-09-16 | 2025-09-23 | 2025-09-23 | On-Time | 0 | High
T464 | Approvals | Vendor Request | Alex | Ops | 2025-09-10 | 2025-09-13 | 2025-09-14 | Delayed | 1 | Medium
T465 | Inventory | Vendor Request | John | IT | 2025-09-06 | 2025-09-12 | 2025-09-12 | On-Time | 0 | Low
T466 | Inventory | System Audit | Alex | Ops | 2025-09-11 | 2025-09-18 | 2025-09-21 | Delayed | 3 | Medium
T467 | Inventory | Policy Review | David | IT | 2025-09-06 | 2025-09-13 | 2025-09-15 | Delayed | 2 | High
T468 | Inventory | Vendor Request | John | IT | 2025-09-07 | 2025-09-11 | 2025-09-13 | Delayed | 2 | Low
T469 | Procurement | System Audit | John | IT | 2025-09-10 | 2025-09-15 | 2025-09-15 | On-Time | 0 | High
T470 | Inventory | Policy Review | Nisha | Procurement | 2025-09-18 | 2025-09-24 | 2025-09-24 | On-Time | 0 | High
T471 | IT | Update Stock DB | Sarah | Ops | 2025-09-03 | 2025-09-08 | 2025-09-11 | Delayed | 3 | Medium
T472 | Reporting | Vendor Request | Alex | Ops | 2025-09-07 | 2025-09-11 | 2025-09-12 | Delayed | 1 | High
T473 | Approvals | Vendor Request | John | IT | 2025-09-13 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Low
T474 | IT | Vendor Request | David | IT | 2025-09-18 | 2025-09-24 | 2025-09-24 | On-Time | 0 | Medium
T475 | Approvals | Data Backup | Priya | Finance | 2025-09-15 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Medium
T476 | Approvals | Server Patch | Priya | Finance | 2025-09-09 | 2025-09-16 | 2025-09-15 | On-Time | -1 | High
T477 | Inventory | Vendor Request | David | IT | 2025-09-12 | 2025-09-19 | 2025-09-21 | Delayed | 2 | Low
T478 | Reporting | System Audit | Alex | Ops | 2025-09-13 | 2025-09-20 | 2025-09-22 | Delayed | 2 | Low
T479 | Approvals | Order Processing | Priya | Finance | 2025-09-16 | 2025-09-21 | 2025-09-20 | On-Time | -1 | Medium
T480 | Inventory | System Audit | Nisha | Procurement | 2025-09-17 | 2025-09-24 | 2025-09-27 | Delayed | 3 | High
T481 | Inventory | Budget Approval | Priya | Finance | 2025-09-06 | 2025-09-10 | 2025-09-10 | On-Time | 0 | High
T482 | Inventory | Policy Review | Alex | Ops | 2025-09-14 | 2025-09-18 | 2025-09-18 | On-Time | 0 | Low
T483 | IT | Data Backup | David | IT | 2025-09-03 | 2025-09-06 | 2025-09-08 | Delayed | 2 | Low
T484 | Approvals | System Audit | John | IT | 2025-09-09 | 2025-09-16 | 2025-09-18 | Delayed | 2 | High
T485 | Procurement | Order Processing | Nisha | Procurement | 2025-09-14 | 2025-09-17 | 2025-09-19 | Delayed | 2 | High
T486 | Reporting | Order Processing | Nisha | Procurement | 2025-09-19 | 2025-09-22 | 2025-09-21 | On-Time | -1 | Low
T487 | Inventory | Server Patch | Nisha | Procurement | 2025-09-12 | 2025-09-18 | 2025-09-19 | Delayed | 1 | Medium
T488 | Approvals | Order Processing | Nisha | Procurement | 2025-09-16 | 2025-09-19 | 2025-09-19 | On-Time | 0 | Medium
T489 | Approvals | Monthly Report | Nisha | Procurement | 2025-09-20 | 2025-09-26 | 2025-09-25 | On-Time | -1 | Medium
T490 | IT | Sprint Update | Alex | Ops | 2025-09-16 | 2025-09-21 | 2025-09-22 | Delayed | 1 | High
T491 | IT | Server Patch | John | IT | 2025-09-09 | 2025-09-15 | 2025-09-14 | On-Time | -1 | High
T492 | Reporting | Server Patch | David | IT | 2025-09-15 | 2025-09-20 | 2025-09-21 | Delayed | 1 | Low
T493 | Approvals | Order Processing | David | IT | 2025-09-03 | 2025-09-07 | 2025-09-09 | Delayed | 2 | High
T494 | Approvals | Budget Approval | Nisha | Procurement | 2025-09-12 | 2025-09-15 | 2025-09-18 | Delayed | 3 | High
T495 | Inventory | Server Patch | David | IT | 2025-09-17 | 2025-09-23 | 2025-09-23 | On-Time | 0 | Low
T496 | Procurement | Update Stock DB | Priya | Finance | 2025-09-07 | 2025-09-11 | 2025-09-10 | On-Time | -1 | High
T497 | Inventory | Budget Approval | Alex | Ops | 2025-09-12 | 2025-09-16 | 2025-09-17 | Delayed | 1 | Medium
T498 | Approvals | System Audit | Sarah | Ops | 2025-09-04 | 2025-09-07 | 2025-09-07 | On-Time | 0 | Medium
T499 | Approvals | Order Processing | Sarah | Ops | 2025-09-06 | 2025-09-12 | 2025-09-15 | Delayed | 3 | Low
T500 | IT | Data Backup | Priya | Finance | 2025-09-09 | 2025-09-12 | 2025-09-13 | Delayed | 1 | High